## Tabelle1
Risk Name | Description | Probability of Occurence | Impact | Factor | Mitigation | Person in Charge of Tracking
Slow Server | Our server is to slow to handle all Userrequests | 75% | 6 | 4.5 | Monitor Serverspeed and use multiple Servers | Sven
Comunication problems | Misunderstandings and a poor information flow beteween teammembers occur | 70% | 6 | 4.2 | If something is unclear ask again. Try to be as detailed as posssible and give all information to the team | Marvin
Inedequate Skills | The team hasn't enough experience to cover their tasks | 40% | 7 | 2.8 | Use technologies which are known by all teammembers | Sven
Motivation problems | teammembers are not motivated and therefor don't fulfill all their tasks | 30% | 9 | 2.7 | Communicate the impact of this issue to all teammembers an get them motivated | Marvin
Loss of teammembers | A team member is ill, exmatriculated or leaves the team. | 5% | 6 | 0.3 | Divide tasks equally so that tasks of lost person can be taken by other people | Tobias
Hardware problems | Development PC fails or malfunctions which will lead to data loss and the team member will not be able to contibute to the project. | 5% | 5 | 0.25 | Maintain hardware and always do backups. | Tobias